## Sheet1
Obsideo Technologies Ltd; Software Development
Suitability Assessment Matrix for using Agile Project Management Techniques on Software Projects
| Characteristic | Low Suitability (score 1) | Moderate Suitability (score 2) | High Suitability (score 3) | Score
1 | Can the users identify a Product Owner who will available throughout the project? | No, or only available part time | yes, but subject to daily operational interruptions | yes, and full time | 0
2 | Do the users understand the principal features of Agile methods? | No, or they do not accept them | Apparently | Yes, and are fully committed | 0
3 | Are the users willing to delegate full authority to the Product Owner? | No; they expect to run meetings to approve proposals | Apparently | Yes, and are fully committed | 0
4 | Will all the team members be assigned to this project full time? | No; many will have other calls on their time during the project | tech team yes, users maybe not | yes , including users | 0
5 | Can the whole project team be co-located | No; key players cannot be co-located | part of the team will remain remote | Yes, and a team room has been identified | 0
6 | Does senior IT management understand the differences between Agile and traditional projects? | No; may be unwilling to fully commit | yes, but wary of the new approaches | Yes, and are fully committed | 0
7 | Are the requirements capable of being broken down into priority packages? | No; monolithic implementation required | yes, but priorities not well-understood | Yes, based upon business benefits | 0
8 | Are the Requirements…. | Stable and well understood | Subject to moderate change during the project | Not stable; subject to frequent change | 0
9 | Is there acceptance of a potential final outstanding backlog? | No; everything must be delivered | yes, but there is a lack of willingness to prioritise the requirements | Yes, and there is a willingness to prioritise to support this
10 | How big will the project be? | Less than 100 staff days | More than 500 staff days | between 100 and 500 staff days | 0
11 | Are there likely to be interfaces with other systems? | with 3 or more other systems |  | with fewer than 3 other systems | 0
12 | Will the project or the product have to comply with external regulations? | Major laws or regulations apply, with penalties for non-compliance | Laws apply, but non-compliance will have limited effect | none, or very limited laws and regulations apply | 0
13 | What development technologies will be involved? | Programming languages and technologies new to company | Programming languages and technologies well-known, but new to organisation | Well-known and established within organisation | 0
14 | Is there likely to be a package solution? | Package solution likely, from non-Agile vendor | Package solution likely, from vendor with genuine Agile experience | Probably no package solution involved | 0
15 | What are the implications for Enterprise Architecture Design? | EA Design likely during the project |  | EA Design will be established before the project starts | 0
16 | What are the implications for Infrastructure changes? | Significant infrastructure build will be required during the project | Some infrastructure build required | Will use existing infrastructure | 0
17 | How prepared is the organisation for Release Management? | no Release Management processes in place |  | Release Management process in place | 0
18 | Are there going to be Legacy or Mainframe components? | Legacy systems and mainframe systems involved | Legacy systems but not mainframe | No legacy or mainframe components | 0
19 | Is this project concerned with web application development? | no |  | yes | 0
20 | How many other projects are affected by this one? | two or more | one | none | 0
|  |  | Total for this Project: |  | 0
Agile Suitability: if the project scores more than 40 it is suitable for Agile.
However, the organisational factors must be taken into account as well as these technical factors